# Board-Level Proposal: AI Customer-Support Chatbot for Mid-Sized E-Commerce

Board Proposal  |  Prepared for: Board of Directors, mid-sized e-commerce company

AI-assisted draft  |  Run ID: 4abbe552e8ac4c8585329f9fd2484e5f  |  Generated: 2026-10-25 18:13 UTC

# Executive Summary

This proposal evaluates the feasibility of deploying an on-premises, 24/7 multilingual AI customer-support chatbot within a $20,000 budget and a four-week timeline. The analysis reveals material conflicts: the required dual-A100 GPU server consumes approximately 60% of the budget, leaving minimal funds for development; the one-week hardware lead time compresses model fine-tuning, integration, and testing into three weeks; and delivering production-quality support across four languages in that window is high-risk. Ongoing human-escalation staffing costs are not included in the project budget. A phased approach targeting a minimal viable product (English + Spanish first, French + German later) is recommended, contingent on immediate board decisions on hardware procurement, team allocation, language scope, and escalation funding.

Budget $20k, 4-week deadline, on-premises only, 24/7 multilingual required.

GPU hardware ~$12k (illustrative) leaves ~$8k for all engineering effort.

Three-week development window after hardware arrival is extremely tight for multilingual fine-tuning and integration.

Human escalation operational cost excluded from project budget.

Recommend MVP with two languages at launch, phased language rollout.

# Feasibility Assessment

Feasibility is marginal under current constraints. The $20,000 cap forces a hardware-first spend that leaves insufficient contingency for development, testing, or scope changes. On-premises hosting adds infrastructure overhead (power, cooling, networking, security hardening) with no dedicated ops staff budgeted. The four-week timeline assumes GPU server delivery and racking in week one; any delay eliminates development time. Multilingual support for four languages requires curated training data, per-language evaluation, and LoRA fine-tuning — unrealistic in three weeks without pre-existing datasets. 24/7 coverage relies on automated chatbot plus an on-call human rotation (cost not in $20k). If the board can approve additional budget, extend timeline, or reduce language scope, feasibility improves significantly.

Budget vs hardware: GPU server ~60% of total, no margin.

Timeline vs multilingual development: 3 weeks for 4 languages is high risk.

On-prem ops: no budget for rack space, power, cooling, security hardening.

Staffing: part-time internal team assumed; no external vendor budget.

Human escalation: ongoing OPEX not captured in project budget.

# Assumptions, Trade-offs & Constraint Conflicts

The following provisional assumptions underpin the proposal. Each is labelled by category and impact. Key trade-offs and constraint conflicts are listed explicitly — the board must decide which to accept, mitigate, or reject.

Assumption: Core team of 2 ML engineers, 1 DevOps, 1 QA, 1 PO available part-time for 4 weeks (assumption).

Assumption: Support volume ~5,000 tickets/month, peak 200 concurrent sessions (illustrative).

Assumption: Target languages English, Spanish, French, German (requires_confirmation).

Assumption: Current systems Shopify, Zendesk, PostgreSQL (assumption).

Assumption: Security requires data residency on-prem, encryption at rest/in transit, GDPR compliance (requires_confirmation).

Assumption: GPU server (2× A100 40GB) procurable and operational in 1 week (constraint_conflict).

Assumption: Illustrative cost breakdown totals $20k with zero contingency (illustrative_data).

Assumption: 24/7 coverage via chatbot + human on-call rotation (1 FTE), cost excluded from $20k (assumption).

Trade-off: Budget vs GPU hardware — consider cloud GPU or smaller model to free funds.

Trade-off: Timeline vs multilingual scope — launch with 2 languages, add 2 post-launch.

Trade-off: On-prem vs limited ops budget — evaluate managed on-prem appliance or colocation.

Trade-off: 24/7 human escalation cost — approve OPEX or accept automated-only off-hours.

# Architecture Overview

Provisional architecture pending board decisions on GPU memory, model variant, and serving stack. On-premises design centers on a dual-A100 GPU server (or alternative) running an open-source LLM (e.g., Llama 3 8B or 70B LoRA fine-tuned) served via vLLM/TGI or equivalent. An internal API gateway handles authentication, rate limiting, and routing. Integration adapters connect to Shopify (order lookup), Zendesk (ticket creation, agent handoff), and PostgreSQL (customer profile). A lightweight chat widget embeds on the storefront. Human escalation triggers on confidence threshold or user request, routing to Zendesk agent workspace with on-call rotation. All data flows remain on-premises; disks encrypted, TLS everywhere, audit logs to SIEM. Network segmentation isolates GPU server, API gateway, and database zones. Key management uses on-prem HSM or sealed secrets. Monitoring via Prometheus/Grafana; model registry and CI/CD via existing MLOps tools if available.

GPU server (2× A100 40GB or alternative) → vLLM/TGI → API gateway → integration adapters.

Multilingual LoRA fine-tune on Llama 3 (variant pending) for EN, ES, FR, DE.

Adapters: Shopify REST/GraphQL, Zendesk API, PostgreSQL direct.

Chat widget → API gateway → model → escalation to Zendesk agent workspace.

Security: disk encryption, TLS, network segmentation, audit logging, HSM keys.

# Phased Implementation Plan

Four-week plan assumes hardware arrival day 1-3 of week 1. The core team is part-time over 4 weeks; critical development compresses into weeks 2-4, creating schedule risk. Any hardware slippage cascades. Week 1 focuses on infrastructure and baseline; weeks 2-3 on multilingual fine-tuning and integration (EN/ES priority, FR/DE if time); week 4 on validation and launch. MVP targets English and Spanish at launch, with French and German phased post-launch.

Week 1: GPU server procurement, racking, OS/hardening, vLLM/TGI deploy, baseline inference test, API gateway scaffold, security baseline (encryption, segmentation, logging).

Week 2: EN/ES dataset prep, LoRA fine-tuning runs, adapter development for Shopify/Zendesk/PostgreSQL, CI/CD pipeline, unit tests.

Week 3: FR/DE dataset prep and fine-tuning (if feasible), integration testing, load testing (200 concurrent), confidence threshold tuning, escalation flow build, documentation.

Week 4: End-to-end UAT, penetration test (if required), GDPR control verification, production cutover, monitoring dashboards live, on-call runbook handoff.

| Week | Key Deliverables | Owner | Risk if Delayed |
| --- | --- | --- | --- |
| 1 | GPU server operational, baseline inference, API gateway, security baseline | DevOps/ML Eng | Compresses all downstream work |
| 2 | EN/ES fine-tuned model, Shopify/Zendesk/PostgreSQL adapters, CI/CD | ML Eng/DevOps | Insufficient time for FR/DE |
| 3 | FR/DE fine-tuning (if feasible), integration & load test, escalation flow | ML Eng/QA | Launch with EN/ES only |
| 4 | UAT, pen test, GDPR check, production launch, monitoring, runbook | All | Launch delay, compliance gaps |

# Illustrative Cost Estimates

All figures are illustrative and assume part-time internal engineering effort over 4 weeks. No external vendor costs included. The budget is fully allocated with zero margin; any scope change or delay will exceed $20,000. Rack, power, and cooling costs for the GPU server are not included in the hardware line and must be funded separately. Penetration testing is not budgeted; an illustrative range is added as a board decision item. Human escalation staffing (1.5-2 FTE for follow-the-sun coverage) estimated $90k-$130k/year — not in project budget.

Human escalation staffing (1.5-2 FTE on-call rotation) estimated $90k-$130k/year — not in project budget.

Cloud GPU alternative could reduce upfront capex but conflicts with on-prem mandate.

Smaller model (7B) on single A100 could save ~$6k hardware but may degrade multilingual quality.

Rack, power, cooling, and physical security costs are excluded and require separate approval.

| Category | Illustrative Cost | Notes |
| --- | --- | --- |
| GPU server (2× A100 40GB) | $12,000 | Hardware only; rack, power, cooling not costed |
| Rack space, power, cooling, physical security | $2,000-$5,000 | Illustrative; requires facilities quote |
| ML engineering (2 engineers × 4 weeks part-time) | $5,000 | Internal cost allocation; assumes existing headcount |
| DevOps / CI-CD / infra | $2,000 | Internal effort |
| QA / validation / load test | $2,000 | Internal effort |
| Project management / documentation | $1,000 | Internal effort |
| Penetration testing (if mandated) | $3,000-$5,000 | Not included in $20k; board decision required |
| Contingency | $1,000 | 5% of budget; likely insufficient |
| Total (excluding pen test & facilities) | $20,000 | No margin for overruns |

# Privacy & Security Risks

On-premises hosting satisfies data residency but introduces operational security burdens. The board must confirm exact GDPR and compliance requirements; current assumptions may be insufficient.

Data residency: all PII stays on-prem — meets requirement if infrastructure is physically secured.

Encryption: AES-256 at rest, TLS 1.3 in transit — required for GDPR Art. 32.

Access control: RBAC on API gateway, model server, database; least privilege for service accounts.

Audit logging: all inference requests, escalation events, admin actions logged to immutable store.

Data retention: policy undefined — must align with GDPR right to erasure and business needs.

Penetration testing: not budgeted; required for production launch if mandated by compliance.

Model inversion / extraction risk: mitigate with rate limiting, output filtering, monitoring.

Key management: on-prem HSM or sealed secrets — procurement and setup not costed.

# Human Escalation Strategy

24/7 coverage combines automated chatbot with a human on-call rotation. The chatbot handles routine queries; escalation triggers on confidence < 0.7, user request, or policy violations (e.g., refund > threshold). Escalations route to Zendesk agent workspace with full conversation context. Sustainable 24/7 coverage requires at least 2 engineers for follow-the-sun or night/weekend shifts (1.5-2 FTE equivalent). Annual cost estimated $90k-$130k (illustrative) — not included in $20k project budget. The board must approve staffing model, shift schedule, and funding before launch.

Escalation triggers: confidence threshold, explicit user request, policy rules.

Routing: Zendesk agent workspace with conversation history and customer data.

On-call rotation: minimum 2 engineers for 24/7; follow-the-sun preferred (1.5-2 FTE).

Cost: illustrative $90k-$130k/year for 1.5-2 FTE equivalent — OPEX, not capex.

Runbook: escalation procedures, SLA targets, handoff checklist — to be delivered week 4.

# Success Metrics & KPIs

Metrics are defined for launch and 90-day post-launch review. Baselines will be established from current Zendesk data once APIs are accessible.

Automated resolution rate: target ≥ 50% of sessions resolved without human escalation (illustrative).

First response time: < 5 seconds for chatbot, < 60 seconds for human escalation.

Customer satisfaction (CSAT): ≥ 4.0/5.0 for chatbot interactions.

Escalation rate: ≤ 30% of sessions (illustrative).

Multilingual parity: per-language resolution rate within 10% of English baseline.

System availability: 99.5% uptime (on-prem hardware dependent).

Latency p95: < 2 seconds end-to-end inference + adapter calls.

Cost per ticket: target reduction vs current human-only baseline (to be measured).

# Board Decisions Required

The following decisions are needed before project kickoff. Each decision unlocks a critical path item.

Approve GPU server procurement ($12k illustrative) and confirm week-1 delivery.

Approve rack, power, cooling, and physical security costs for on-prem GPU server (illustrative $2k-$5k).

Confirm target languages for MVP (recommend EN+ES only) and quality thresholds per language.

Approve human escalation staffing model (minimum 2 engineers for follow-the-sun) and annual OPEX budget ($90k-$130k illustrative).

Finalize security/compliance requirements (GDPR controls, audit logging, data retention, penetration testing scope).

Confirm team composition, availability, and allocation for 4-week sprint.

Provide current system API specs and data schemas for Shopify, Zendesk, PostgreSQL.

Decide on contingency plan if hardware delayed: cloud burst, timeline extension, or scope reduction.

Authorize use of existing on-prem MLOps tools (model registry, CI/CD, monitoring) or approve procurement.

Select Llama 3 variant (7B, 8B, 70B) based on GPU memory and latency targets.

Confirm availability of curated multilingual training data for all four languages or approve data creation effort.

Approve penetration testing scope and budget ($3k-$5k illustrative) if mandated by compliance.

Define data retention policy aligned with GDPR right to erasure and business needs.

Confirm key management approach (on-prem HSM vs sealed secrets) and approve any procurement.

Accept zero-margin budget risk and agree on change control process for scope adjustments.

Approve phased language rollout: EN/ES at launch, FR/DE post-launch.

Acknowledge that human escalation OPEX is separate from project capex and commit to funding.

Sign off on risk register and mitigation plans, accepting residual risks.

# Risks, Mitigations & Open Questions

Top risks with mitigations and the open questions that must be resolved. All 18 open questions from the plan are reflected below.

| Risk | Likelihood | Impact | Mitigation | Open Question |
| --- | --- | --- | --- | --- |
| GPU server delivery > 1 week | High | Critical — compresses dev to <3 weeks | Pre-order with penalty clause; identify cloud fallback | Has procurement been approved? Can delivery be guaranteed week 1? |
| Multilingual quality insufficient in 3 weeks | High | High — launch with degraded FR/DE | Phase languages: EN/ES launch, FR/DE post-launch | Are curated datasets available for all 4 languages? |
| Budget overrun (zero contingency) | Medium | Critical — project halt | Strict scope lock; weekly burn-rate review | Will board approve contingency fund or scope reduction? |
| On-prem ops gaps (cooling, power, security) | Medium | High — compliance failure | Engage facilities/security early; document gaps | What are exact physical and security requirements? |
| Human escalation staffing unfunded | High | High — 24/7 SLA breach | Board to approve OPEX before kickoff | What is approved staffing model and budget? |
| Integration API mismatches | Medium | Medium — delays | Early API discovery sprint week 1 | What are exact Shopify/Zendesk/PostgreSQL API specs? |
| Llama variant selection (7B/8B/70B) undecided | Medium | High — affects GPU memory, latency, quality | Benchmark variants week 1; decide by end of week 1 | Which Llama 3 variant fits GPU memory and latency requirements? |
| Curated multilingual training data unavailable | High | High — delays fine-tuning, reduces quality | Allocate week 1 for data collection/creation; use synthetic if needed | Is curated multilingual training data available for all four languages, or must it be created? |
| GDPR/compliance controls undefined | Medium | High — legal exposure | Engage legal/compliance week 1; document required controls | What are the precise GDPR and on-prem security controls required (audit logging, data retention, penetration testing)? |
| Existing MLOps tools unknown | Low | Medium — duplicate effort if not reused | Inventory on-prem tools week 1 | Are there existing on-prem MLOps tools (model registry, CI/CD, monitoring) that can be reused? |
| Penetration testing scope and cost not approved | Medium | Medium — launch delay if mandated | Add as board decision with illustrative cost | Is penetration testing required for launch? What is the scope and budget? |
| Team composition and availability not confirmed | High | Critical — resource gaps | Confirm allocations before kickoff | What is the final confirmed team composition and availability? |
| Target languages and quality thresholds not confirmed | High | High — scope creep | Board to confirm MVP languages (EN/ES) and thresholds | What are the exact target languages and required quality thresholds per language? |
| Security/compliance requirements not finalized | Medium | High — rework | Finalize requirements week 1 | What are the precise security and compliance requirements (e.g., data-retention, audit logging, penetration testing)? |
| GPU server procurement approval pending | High | Critical — schedule | Board to approve immediately | Is there approval and budget for procuring the GPU server within the first week? |
| Human escalation staffing model undefined | High | High — 24/7 coverage gap | Board to approve model and budget | What is the approved human escalation staffing model (on-call rotation size, shift coverage) and its annual cost? |
| Rack/power/cooling costs not budgeted | Medium | Medium — unexpected capex | Facilities to provide quote week 1 | What are the rack, power, cooling, and physical security costs for the GPU server? |
| Model inversion/extraction risk | Low | Medium — data leakage | Rate limiting, output filtering, monitoring | What are the acceptable rate limits and monitoring thresholds for model protection? |

# Known Facts (Provided in the Request)

Total budget is $20,000.

Requirement for 24/7 multilingual customer support.

Hosting must be on-premises.

Target launch within 4 weeks.

Company is a mid-sized e-commerce business.

Teams, expected support volume, supported languages, current systems, and security requirements have not yet been decided.

# Assumptions and Open Questions

| Type | Statement | Impact |
| --- | --- | --- |
| Assumption | A core team of 2 ML engineers, 1 DevOps engineer, 1 QA engineer, and 1 product owner will be available part‑time for the 4‑week period. | Determines effort allocation for model fine‑tuning, integration, testing, and documentation. |
| Illustrative data | Expected support volume is approximately 5,000 tickets per month with a peak of 200 concurrent chat sessions. | Drives GPU sizing, latency targets, and autoscaling decisions. |
| Requires confirmation | Supported languages will be English, Spanish, French, and German (4 languages). | Affects model selection, training data preparation, evaluation effort, and cost. |
| Assumption | Current systems include a Shopify storefront, Zendesk ticketing, and a PostgreSQL customer database. | Defines integration points, API availability, and data‑flow design. |
| Requires confirmation | Security requirements mandate data residency on‑premises, encryption at rest and in transit, and GDPR compliance. | Influences architecture (e.g., network segmentation, key management) and audit readiness. |
| Constraint conflict | An on‑premises GPU server (2× NVIDIA A100 40 GB) can be procured, racked, and operational within 1 week. | Hardware cost (~$12k) consumes >50% of budget; 1‑week lead time leaves only 3 weeks for development, creating a schedule risk. |
| Illustrative data | Illustrative cost breakdown: GPU server $12,000; open‑source model licensing $0; integration development $5,000; testing & validation $2,000; contingency $1,000 = $20,000 total. | Shows budget fully allocated with no margin; any scope change or delay will exceed budget. |
| Assumption | 24/7 coverage will be achieved by the automated chatbot with a human on‑call rotation (1 FTE) for escalation; human staffing cost is not included in the $20k budget. | Highlights an ongoing operational cost outside the project budget that the board must approve. |
| Constraint conflict | Budget vs on-prem GPU hardware cost. | Identified during analysis; may require trade-off decisions. |
| Constraint conflict | Timeline vs hardware procurement and multilingual model development. | Identified during analysis; may require trade-off decisions. |
| Constraint conflict | On-prem hosting vs limited budget for infrastructure and ops. | Identified during analysis; may require trade-off decisions. |
| Constraint conflict | 24/7 multilingual requirement vs budget and timeline. | Identified during analysis; may require trade-off decisions. |
| Constraint conflict | No budget margin for scope changes or delays. | Identified during analysis; may require trade-off decisions. |
| Constraint conflict | Human escalation operational cost excluded from project budget. | Identified during analysis; may require trade-off decisions. |
| Constraint conflict | GPU hardware cost ($12k) vs. total budget ($20k) leaves minimal development funds. | Identified during analysis; may require trade-off decisions. |
| Constraint conflict | One-week hardware lead time vs. four-week deadline compresses development to three weeks. | Identified during analysis; may require trade-off decisions. |
| Constraint conflict | Multilingual fine-tuning and evaluation for four languages vs. three-week development window. | Identified during analysis; may require trade-off decisions. |
| Constraint conflict | On-premises infrastructure (power, cooling, networking, security hardening) vs. limited budget and no dedicated ops staff. | Identified during analysis; may require trade-off decisions. |
| Constraint conflict | 24/7 human escalation staffing cost excluded from project budget, creating ongoing operational expense. | Identified during analysis; may require trade-off decisions. |

## Open questions

What is the final confirmed team composition and availability?

What are the exact target languages and required quality thresholds per language?

What are the current system APIs and data schemas for Shopify, Zendesk, and the customer DB?

What are the precise security and compliance requirements (e.g., data‑retention, audit logging, penetration testing)?

Is there approval and budget for procuring the GPU server within the first week?

What is the acceptable human escalation staffing model and its cost?

Are there any existing ML infrastructure or MLOps tools on‑premises that can be reused?

What is the final team composition and availability?

What are the exact target languages and quality thresholds?

What are the current system APIs and data schemas?

What are the precise security and compliance requirements?

Is there approval and budget for GPU server procurement in week 1?

Are there existing on-prem ML infrastructure or MLOps tools?

Which Llama 3 variant (7B, 8B, 70B) fits the GPU memory and latency requirements?

Is curated multilingual training data available for all four languages, or must it be created?

What are the exact Shopify, Zendesk, and PostgreSQL API specifications and authentication mechanisms?

Has the GPU server procurement been approved and can it be delivered and racked within week 1?

What are the precise GDPR and on-prem security controls required (audit logging, data retention, penetration testing)?

What is the approved human escalation staffing model (on-call rotation size, shift coverage) and its annual cost?

Are there existing on-prem MLOps tools (model registry, CI/CD, monitoring) that can be reused?

## Unresolved review findings

Final team composition and availability not confirmed

Exact target languages and quality thresholds per language not decided

Current system API specs and data schemas for Shopify, Zendesk, PostgreSQL not provided

Precise security/compliance requirements (GDPR controls, audit logging, data retention, pen test scope) not finalized

GPU server procurement approval and week-1 delivery guarantee pending

Rack, power, cooling, physical security costs not quoted

Human escalation staffing model, shift coverage, and annual budget not approved

Llama 3 variant selection (7B/8B/70B) pending benchmark

Availability of curated multilingual training data for all four languages unknown

Existence of on-prem MLOps tools (model registry, CI/CD, monitoring) not inventoried

Board acceptance of zero-margin budget risk and change control process not recorded

# AI-Assisted Generation Disclosure and Human-Review Notice

This document was generated with AI assistance (provider: openrouter, model: nvidia/nemotron-3-ultra-550b-a55b:free). Content, including any figures marked as illustrative, has not been independently verified.

Decisions with legal, financial, security, operational or other significant consequences require review and approval by a qualified person before this document is relied upon.