# Board Proposal: AI Customer Support Chatbot for Mid-Sized E-Commerce Company

Board Proposal  |  Prepared for: Board of Directors

AI-assisted draft  |  Run ID: e9ecf5664bcf41999c1f1307af515c65  |  Generated: 2026-10-25 18:35 UTC

# Executive Summary

This proposal evaluates an AI customer‑support chatbot for a mid‑sized e‑commerce business under a $20,000 budget, a four‑week launch window, on‑premises hosting, and 24/7 multilingual support. Feasibility analysis shows that the combined illustrative cost of minimum GPU hardware ($10,000) and engineering effort ($12,000) already exceeds the budget before integration, testing, and operations. A full five‑language, high‑availability, PCI‑DSS/GDPR‑hardened deployment would require roughly $32,000–$40,000 and 8–10 weeks. The only configuration that fits the current constraints is an English‑only minimum viable product on a single GPU (or quantized CPU) with best‑effort 24/7 coverage, delivered in about three weeks for approximately $15,000. The board must decide whether to reduce scope, increase budget, extend the timeline, or adopt a hybrid cloud/on‑premises model.

Budget cap $20,000; illustrative baseline cost $22,000 (hardware + engineering) — exceeds cap

Four‑week timeline insufficient for multilingual fine‑tuning, HA setup, and compliance hardening

Recommended Phase 1: English‑only MVP on existing or single GPU infrastructure

Phase 2 (optional): add languages, HA, full compliance after budget/timeline approval

# Feasibility Analysis & Key Trade-offs

Assumption: a core team of 2‑3 engineers (ML, backend, DevOps) is available part‑time for four weeks. Assumption: initial volume 500‑1,000 conversations/day across five languages (English, Spanish, French, German, Mandarin) (illustrative). Assumption: integration with a ticketing system (e.g., Zendesk) and product DB via REST APIs. Assumption: security baseline aligns with PCI‑DSS and GDPR. Constraint conflict: hardware ($10k) + engineering ($12k) = $22k > $20k cap, leaving no room for integration, testing, ops, or contingency. Constraint conflict: four weeks cannot accommodate custom multilingual model tuning, RAG pipeline, on‑prem hardening, and 24/7 operational validation simultaneously. Constraint conflict: true 24/7 on‑prem availability requires redundant hardware, backup power, and staffed on‑call — not scoped or budgeted. Trade‑off: open‑source LLM (Llama 3 8B) avoids per‑token fees but needs GPU infrastructure and ML expertise. Trade‑off: translation layer (fast, quality loss) versus fine‑tuning (higher quality, 2‑3 weeks extra). Trade‑off: hybrid cloud/on‑prem meets budget/timeline but violates strict on‑prem requirement.

Budget vs. hardware: GPU cluster consumes 50% of budget

Budget vs. engineering: 120h @ $100/h = $12k exceeds remainder

Timeline vs. scope: multilingual quality evaluation adds 1‑2 weeks per language

On‑prem 24/7 vs. HA: redundant servers, power, on‑call not budgeted

Security hardening vs. timeline: PCI‑DSS/GDPR validation adds 2‑4 weeks

# Provisional Assumptions & Open Questions

The following provisional assumptions drive the analysis. Each is labelled Assumption: and marked (illustrative) where numbers are invented. Open questions must be resolved before final commitment.

Assumption: 2‑3 engineers available part‑time for 4 weeks (illustrative)

Assumption: 500‑1,000 conversations/day across 5 languages (illustrative)

Assumption: Supported languages English, Spanish, French, German, Mandarin (illustrative)

Assumption: Current systems include Zendesk ticketing and product DB via REST APIs

Assumption: Security requirements align with PCI‑DSS and GDPR (illustrative)

Assumption: Human escalation path assumes existing agents can be trained in 1 week

Open Question: Exact composition and availability of implementation team?

Open Question: Projected daily/peak conversation volume and seasonal variation?

Open Question: Which languages required at launch vs. later phases?

Open Question: Current ticketing, CRM, product systems — APIs documented?

Open Question: Precise security/compliance requirements (PCI‑DSS level, GDPR, CCPA)?

Open Question: Existing on‑prem GPU infrastructure or need to procure?

Open Question: Acceptable latency and uptime SLA for chatbot?

Open Question: Data storage, retention, deletion policies for privacy regulations?

Open Question: Board tolerance for phased rollout (English first)?

Open Question: Can budget be increased or timeline extended?

# Architecture Overview

Three on‑premises architecture options were evaluated. All exceed the $20k/4‑week constraints for full multilingual 24/7 support. Option A — vLLM serving Llama 3 8B on 2× A10G GPUs with a translation layer (e.g., NLLB) for non‑English languages; fastest to implement but adds latency and quality risk. Option B — fine‑tuned multilingual Llama 3 8B / BLOOMZ on same hardware; better quality but needs 2‑3 weeks for data preparation and tuning, pushing launch beyond four weeks. Option C — hybrid: on‑prem English model plus cloud API for other languages; meets budget/timeline but violates strict on‑prem requirement. The minimal viable architecture for Phase 1 is a single GPU (or 4‑bit quantized model on CPU) running an English‑only Llama 3 8B with a basic RAG pipeline, integrated to the ticketing system via REST, with logging, encryption at rest/in transit, and a simple health‑check monitor.

Option A: vLLM + translation layer — fast, quality risk

Option B: Fine‑tuned multilingual model — higher quality, +2‑3 weeks

Option C: Hybrid cloud/on‑prem — meets constraints, breaks on‑prem rule

Phase 1 baseline: English‑only, single GPU/CPU, basic RAG, best‑effort 24/7

# Phased Implementation Plan

The plan splits delivery into two phases. Phase 1 targets an English‑only MVP within three weeks and $15k (illustrative). Phase 2 adds multilingual support, high availability, and full compliance contingent on board approval of additional budget and time.

Phase 1 fits current budget and timeline if scope is limited to English

Phase 2 requires board decision on budget increase and timeline extension

| Phase | Duration | Scope | Key Deliverables | Illustrative Cost |
| --- | --- | --- | --- | --- |
| Phase 1 – MVP | Weeks 1‑3 | English only; single GPU or quantized CPU; basic RAG; ticketing integration; logging & encryption; best‑effort 24/7 monitoring | Chatbot endpoint, integration test, agent handoff playbook, monitoring dashboard | $15,000 (illustrative) |
| Phase 2 – Expansion | Weeks 5‑10 (contingent) | Add 4 languages via fine‑tuning or translation layer; HA pair of GPUs; backup power; staffed on‑call; PCI‑DSS/GDPR hardening; penetration test | Multilingual models, HA deployment, compliance artifacts, updated runbooks | $25,000‑$30,000 (illustrative) |

# Illustrative Cost Estimates

All figures are labelled (illustrative) and represent provisional sizing based on the assumptions above. They are not quotes.

Baseline hardware + engineering ($22k) already exceeds $20k cap

Phase 1 MVP stays within cap by reducing hardware to one GPU and deferring HA

Full compliance and multilingual support push total to $33k+ (illustrative)

| Item | Quantity | Unit Cost (illustrative) | Total (illustrative) |
| --- | --- | --- | --- |
| GPU servers (A10G‑class) | 2 | $5,000 | $10,000 |
| Engineering effort (120 h @ $100/h) | 1 | $12,000 | $12,000 |
| Integration & testing | 1 | $5,000 | $5,000 |
| Ops setup (monitoring, on‑call, backup power) | 1 | $3,000 | $3,000 |
| Contingency (10%) | 1 | $3,000 | $3,000 |
| Total (full multilingual HA) |  |  | $33,000 |
| Phase 1 MVP (single GPU, no HA, English only) |  |  | $15,000 |

# Privacy & Security Risk Assessment

Key risks and mitigations for on‑premises deployment handling customer PII and payment data.

Risk: PII/payment data logged in chat transcripts — Mitigation: encrypt logs at rest and in transit; enforce strict RBAC; implement automated redaction before storage

Risk: Model inversion or prompt injection — Mitigation: input sanitization, output filtering, rate limiting, anomaly detection

Risk: Data residency violation — Mitigation: on‑prem hosting satisfies residency; ensure physical security of server room

Risk: Insufficient audit trail for PCI‑DSS/GDPR — Mitigation: immutable audit logs, centralized SIEM integration, quarterly log review

Risk: Unpatched OS/container vulnerabilities — Mitigation: automated patch management, container image scanning, hardened base images

Risk: Retention/deletion non‑compliance — Mitigation: configurable retention policies, automated purge jobs, data‑subject request API

# Human Escalation Strategy

Assumption: existing support agents can be trained in one week to handle chatbot handoffs. The escalation flow: chatbot detects intent confidence below threshold or explicit user request → creates ticket in Zendesk with conversation context → routes to next available agent pool (24/7 shift) → agent resolves and closes ticket → feedback loop updates chatbot training data. A runbook defines escalation triggers, SLA for agent response (target <5 min), and handoff UI. Training includes chatbot UI, context viewing, and fallback procedures. If agent capacity is insufficient, a supplemental on‑call rotation must be budgeted.

Trigger: low confidence, user request, policy violation

Ticket creation with full conversation context

Routing to 24/7 agent pool (existing staff)

Target agent response <5 min (illustrative)

Feedback loop for continuous improvement

# Success Metrics & KPIs

Metrics will be tracked from launch and reviewed weekly.

Deflection rate: % of conversations resolved without human agent (target ≥30% Phase 1)

Customer Satisfaction (CSAT) score: post‑chat survey (target ≥4.0/5)

Average handling time (AHT) for escalated tickets (target ≤8 min)

First‑contact resolution (FCR) for chatbot‑only interactions (target ≥70%)

System uptime: % availability of chatbot endpoint (target 99.5% best‑effort Phase 1)

Latency p95: response time <2 s (illustrative SLA)

Error rate: % of conversations with fallback or failure (target <2%)

Multilingual quality (Phase 2): BLEU/human eval per language ≥0.8

# Board Decisions Required

The board must resolve the following before proceeding.

Approve Phase 1 MVP scope (English only) within $20k and 4 weeks, or authorize budget increase for broader scope

Decide on tolerance for phased rollout (English first, languages added monthly)

Confirm whether a hybrid cloud/on‑prem architecture is acceptable

Determine acceptable latency and uptime SLA for the chatbot

Specify exact PCI‑DSS SAQ level and whether a QSA audit is required

Confirm existing on‑prem GPU availability or authorize procurement

Authorize extension of current on‑call rotation or fund new on‑call staffing

Set policy on data retention, deletion, and privacy‑request handling

# Risks, Conflicts & Remaining Uncertainties

Material conflicts identified during analysis remain unresolved. They are restated here for visibility.

Budget vs. hardware + engineering: $22k baseline exceeds $20k cap

Timeline vs. multilingual quality: 4 weeks insufficient for 5‑language evaluation

On‑prem 24/7 vs. HA requirements: redundant hardware, power, on‑call not scoped

Security hardening vs. timeline: PCI‑DSS/GDPR validation adds 2‑4 weeks

Open questions on team composition, volume, languages, systems, compliance, hardware, SLA, data policy, phased rollout tolerance, budget/timeline flexibility

Uncertainty whether quantized CPU inference meets latency SLA

Uncertainty whether existing monitoring can absorb chatbot without new hires

# Recommendations & Next Steps

Based on the feasibility analysis, the recommended path is to launch an English‑only MVP (Phase 1) within the current budget and timeline, then evaluate expansion.

Approve Phase 1 MVP (English, single GPU/CPU, basic RAG, best‑effort 24/7) — $15k, 3 weeks (illustrative)

Assign a project lead and confirm engineering availability this week

Procure or allocate one GPU server (or validate CPU quantized model) immediately

Begin integration with ticketing API and define escalation runbook

Schedule board review at end of Week 3 to decide on Phase 2 funding and scope

Resolve open questions on compliance level, SLA, and data policy before Phase 2 kickoff

If board requires full multilingual 24/7 at launch, approve budget increase to ≥$33k and timeline extension to ≥8 weeks

# Known Facts (Provided in the Request)

Total budget is $20,000

Requirement: 24/7 multilingual support

Requirement: on-premises hosting

Launch timeline: within 4 weeks

Company is a mid-sized e-commerce business

Teams involved, expected support volume, supported languages, current systems, and security requirements have not yet been decided

# Assumptions and Open Questions

| Type | Statement | Impact |
| --- | --- | --- |
| Assumption | A small core team of 2-3 engineers (ML, backend, DevOps) is available part-time for the 4-week period. | Determines personnel cost and feasibility of custom development vs. off-the-shelf solutions. |
| Illustrative data | Expected initial support volume is 500-1,000 conversations per day across 5 languages. | Drives hardware sizing, model selection, and licensing costs for multilingual capabilities. |
| Illustrative data | Supported languages: English, Spanish, French, German, and Mandarin (top 5 by traffic). | Affects model choice, translation layers, and evaluation effort. |
| Assumption | Current systems include a ticketing system (e.g., Zendesk) and a product database accessible via REST APIs. | Influences integration complexity and data privacy scope. |
| Assumption | Security requirements align with PCI-DSS and GDPR for customer data handling. | Dictates encryption, access controls, audit logging, and data residency needs for on-premises deployment. |
| Illustrative data | Illustrative hardware cost: 2x GPU servers (e.g., NVIDIA A10G) at $5,000 each for 4-week rental/purchase amortization. | Major budget consumer; may conflict with $20k cap when combined with software and personnel. |
| Illustrative data | Illustrative software cost: Open-source LLM (e.g., Llama 3 8B) with fine-tuning and RAG setup; estimated engineering effort 120 hours at $100/hr = $12,000. | Shows likely budget overrun; highlights need for phased or reduced scope. |
| Constraint conflict | Constraint conflict: 24/7 on-premises multilingual support with custom LLM likely exceeds $20k budget and 4-week timeline. | Board must decide on scope reduction, budget increase, timeline extension, or hybrid cloud/on-prem approach. |
| Assumption | Human escalation path assumes existing customer support agents can be trained in 1 week to handle chatbot handoffs. | Affects operational readiness and training costs. |
| Constraint conflict | Budget vs. hardware: Minimum viable on-prem GPU cluster (~$10k) consumes 50% of budget, leaving $10k for all software, integration, testing, and ops. | Identified during analysis; may require trade-off decisions. |
| Constraint conflict | Budget vs. engineering: Estimated 120 engineering hours at market rates ($12k) exceeds remaining budget after hardware. | Identified during analysis; may require trade-off decisions. |
| Constraint conflict | Timeline vs. scope: 4 weeks cannot accommodate custom multilingual model tuning, RAG development, security hardening, and 24/7 operational validation simultaneously. | Identified during analysis; may require trade-off decisions. |
| Constraint conflict | On-premises vs. 24/7 support: True 24/7 on-prem availability requires HA pairs, backup power, and staffed on-call — not scoped in current assumptions. | Identified during analysis; may require trade-off decisions. |
| Constraint conflict | Multilingual vs. timeline: Quality evaluation across 5 languages at launch adds 1-2 weeks minimum for test sets and human review per language. | Identified during analysis; may require trade-off decisions. |
| Constraint conflict | Budget vs. hardware+engineering: Baseline $22k (GPU + engineering) exceeds $20k cap before integration, testing, ops. | Identified during analysis; may require trade-off decisions. |
| Constraint conflict | Timeline vs. multilingual quality: 4 weeks insufficient for data curation, fine‑tuning, and human evaluation across 5 languages. | Identified during analysis; may require trade-off decisions. |
| Constraint conflict | On‑prem 24/7 vs. HA requirements: True 24/7 needs redundant hardware, backup power, and staffed on‑call — not scoped or budgeted. | Identified during analysis; may require trade-off decisions. |
| Constraint conflict | Security hardening vs. timeline: PCI‑DSS/GDPR validation (encryption, access controls, audit logs, penetration testing) typically adds 2–4 weeks. | Identified during analysis; may require trade-off decisions. |

## Open questions

What is the exact composition and availability of the implementation team?

What is the projected daily/peak conversation volume and seasonal variation?

Which specific languages must be supported at launch vs. later phases?

What are the current ticketing, CRM, and product systems? Are APIs documented and accessible?

What are the precise security and compliance requirements (PCI-DSS level, GDPR, CCPA, etc.)?

Is there existing on-premises GPU infrastructure, or must hardware be procured?

What is the acceptable latency and uptime SLA for the chatbot?

How will conversation data be stored, retained, and deleted to meet privacy regulations?

What is the board's tolerance for phased rollout (e.g., English-only first, then multilingual)?

Can the budget be increased or timeline extended if feasibility analysis shows gaps?

What is the exact composition and availability of the implementation team (ML, backend, DevOps)?

Is there existing on‑prem GPU infrastructure that can be repurposed (reducing hardware cost)?

Can quantized models (e.g., 4‑bit Llama 3 8B) run acceptably on CPU‑only servers to avoid GPU spend?

What is the acceptable latency SLA (e.g., <2 s p95) for chatbot responses?

Will the board approve a phased launch (English first, languages added monthly)?

What exact PCI‑DSS SAQ level applies (A, A‑EP, D) and is a QSA audit required?

Can existing monitoring/on‑call rotation be extended to cover the chatbot without new hires?

What is the board’s tolerance for a hybrid cloud/on‑prem architecture if it meets budget and timeline?

## Unresolved review findings

Document review could not be completed; the draft has not passed the review stage.

# AI-Assisted Generation Disclosure and Human-Review Notice

This document was generated with AI assistance (provider: openrouter, model: nvidia/nemotron-3-ultra-550b-a55b:free). Content, including any figures marked as illustrative, has not been independently verified.

Decisions with legal, financial, security, operational or other significant consequences require review and approval by a qualified person before this document is relied upon.